CEBU INSTITUTE OF TECHNOLOGY

UNIVERSITY

COLLEGE OF COMPUTER STUDIES

Software Project Management Plan

for

CeView

Version: Beta Testing (Refactored SPMP, Semester 2)

[Course code / section]  ·  [Adviser]  ·  [Team members]

How to read this draft

Highlighted text in [square brackets] marks information the team has not yet supplied or confirmed. Grey text in parentheses (like this) identifies the source of a statement: a repository file, commit, or pull request, or the team answers given on 19 September 2026. Statements with no source marker describe what this plan commits the team to, and were confirmed by the team.

Repository evidence comes from branch ph2-dev of SherieHub/CeView at commit 5116a161 (14 Sep 2026). The team confirmed ph2-dev as the current baseline. GitHub Issues, pull-request discussions, and Jira were not accessible when this plan was written. They are not used as evidence.

TABLE OF CONTENTS

1. Overview	4

1.1. Project Summary	4

1.1.1. Purpose, scope and objectives	4

1.1.2. Assumptions and constraints	5

1.1.3. Project deliverables	5

1.1.4. Schedule and budget summary	6

1.2. Evolution of plan	7

2. References	7

3. Definitions	7

4. Project organization	8

4.1. External structure	8

4.2. Internal structure	8

4.3. Roles and responsibilities	9

5. Managerial process plans	9

5.1. Start-up plan	9

5.1.1. Estimation plan	9

5.1.2. Staffing plan	9

5.1.3. Resource acquisition plan	10

5.1.4. Project staff training plan	10

5.2. Work plan	10

5.2.1. Work activities	10

5.2.2. Schedule allocation	11

5.2.3. Resource allocation	12

5.2.4. Budget allocation	12

5.3. Control plan	13

5.3.1. Requirements control plan	13

5.3.2. Schedule control plan	13

5.3.3. Budget control plan	13

5.3.4. Quality control plan	13

5.3.5. Reporting plan	14

5.3.6. Metrics collection plan	14

5.3.7. Risk management plan	14

5.3.8. Project closeout plan	15

6. Technical process plans	15

6.1. Process Model	15

6.2. Methods, tools, and techniques	16

6.3. Infrastructure Plan	16

6.3. Product Acceptance Plan	17

7. Supporting process plans	18

7.1. Configuration management plan	18

7.2. Verification and validation plan	18

7.3. Documentation plan	19

7.4. Quality assurance plan	19

7.5. Reviews and audits	19

7.6. Problem resolution plan	20

7.7. Subcontractor management plan	20

7.8. Process improvement plan	20

8. Additional Plans	20

9. Plan Annexes	20

Annex A. Repository evidence summary (ph2-dev @ 5116a161)	20

Annex B. Assumptions & Open Questions	21

10. Index	21

# 1.  Overview

## 1.1.  Project Summary

### 1.1.1.  Purpose, scope and objectives

Purpose. CeView is a tourism-demand intelligence and AI-assisted marketing platform for Cebu-based tourism MSMEs such as dive shops, cafés, and tour operators. It forecasts inbound-traveler demand surges from specific international markets and alerts business owners when a surge is coming. It helps them draft, review, and publish market-localized content around the surge, then reports on how that content performed.

Product structure. The product is organized into four modules:

- Module 1 — Business Classification & Uniqueness Scoring (1.1 Business Input, 1.2 Uniqueness Scoring).

- Module 2 — Market Radar & Notifications (2.1 Market Data Ingestion, 2.2 Market Radar / AI forecasting pipeline). The official forecasting design is the BiLSTM + Transformer demand model hosted on Hugging Face Spaces

- Module 3 — Content Studio (3.1 Content Generation, 3.2 Creative Direction, 3.3 Compliance).

- Module 4 — Campaign Analytics & Reporting (4.1 Campaign Engagement Metrics, 4.2 Promotional Effectiveness Score, 4.3 AI-Generated Prescriptive Performance Report). Includes read-only Meta Ads and TikTok Ads connections

Scope of this plan (Semester 2). This plan covers Semester 2 of the project: 18 weeks running from MVP validation to final defense and endorsement. The approved scope is Modules 1–4 as currently implemented, plus the following additions:

- Content Studio → Meta Lead Ads campaign setup. Operators create Meta lead-generation ad campaigns from content produced in the Content Studio.

- Marketing attribution → Surge alerts produce attribution codes, captions carry the codes, and bookings are tied back to campaigns and reported in Module 4.

- Paid usage. CeView will accept payment from customers. It will offer a free tier, and better performance (stronger models) will require payment.

Explicitly out of scope:

- TikTok campaign creation, excluded because of expense

- Organic (non-ad) posting to Facebook/Instagram Pages

Objectives. The course breakdown defines these Semester 2 outcomes

- Validate the Semester 1 MVP with users and customers, and refine the scope and success metrics.

- Deliver a feature-complete, deployed system with performance, security, and scalability improvements.

- Complete functional, integration, system, usability, and acceptance testing with pilot MSMEs.

- Onboard paying customer(s), and collect proof of usage and payment.

- Produce the research paper, business model canvas, and pitch deck, then pass the technical, research, and commercial defense.

- Obtain endorsement for incubation, publication, or scaling.

Measurable success metrics: [success metrics refined during MVP validation — reference the MVP Validation Report].

Official statement of requirements: Refactored Software Requirements Specification (SRS), [SRS version / location].

### 1.1.2.  Assumptions and constraints

Constraints.

- Schedule. Semester 2 runs 18 weeks. Document submission deadlines are fixed by the course (see 1.1.4). Where the course weekly breakdown and the submission table differ, the submission table governs the document due dates and the breakdown governs all other phase timing.

- Technology is already established in the codebase:

  - React 19

  - TypeScript

  - Vite

  - Tailwind

  - Spring Boot 3.3 (Java 21) with JWT auth

  - Python 3.12 FastAPI services (fastapi-sbert, fastapi-transformer)

  - PostgreSQL 16 + pgvector with Flyway migrations.

- Forecasting. The deployed system runs the BiLSTM forecasting engine (FORECAST_ENGINE=bilstm)

- The model needs 52 weeks of history, and ingestion backfills 52 weeks. The engine fails loudly instead of padding the missing history.

- Hosting. The production system is hosted on Amazon Web Services (AWS), replacing the Render setup in render.yaml (see 6.3). The forecasting model itself stays on Hugging Face Spaces.

- Paid external services. SerpApi, AWS hosting, and Hugging Face model hosting are paid costs. Amounts: [budget figures].

- Free-tier dependency. Groq, the LLM provider for content generation and reports, is used on its free tier (Project team, 19 Sep 2026). Free-tier rate and usage limits apply (see risk R10).

- Multi-tenant isolation. Every data-access path must be scoped to the authenticated business operator.

- Meta platform access. Creating Lead Ads campaigns needs Meta Marketing API permissions beyond the current read-only ads_read scope.

Assumptions.

- Pilot MSMEs will be available for validation, usability, and acceptance testing in Weeks 8–9, and for actual usage in Weeks 11–12. [number and names of pilot MSMEs]

- Week 1 of Semester 2 began on 16 August 2026, derived from the course due dates (Week 4 ends 12 Sep; Week 5 ends 19 Sep). [confirm semester start date]

- [Additional assumptions, e.g., team availability, adviser availability]

### 1.1.3.  Project deliverables

The deliverables below come from the course weekly breakdown and submission table (Project team (answers of 19 Sep 2026)). Delivery medium and location: [e.g., course LMS submission link].

| Deliverable | Due / Week | Source |
| --- | --- | --- |
| MVP Validation Report | Sep 12, 2026, 11:59 PM (Week 1–4) | Submission table |
| Refactored SRS | Sep 19, 2026, 11:59 PM (Week 5) | Submission table |
| Refactored SPMP (this document, Beta) | Sep 19, 2026, 11:59 PM (Week 5) | Submission table |
| Refactored SDD | Sep 19, 2026, 11:59 PM (Week 5) | Submission table |
| Updated traceability matrix | Week 3 per breakdown; [confirm due date] | Weekly breakdown |
| Software Test Document (STD): test plan and test cases | Sep 26, 2026, 11:59 PM (Week 6) | Submission table |
| Feature-complete system and implementation reports | Weeks 4–7 per breakdown; ph3-dev work Weeks 6–9 (see 5.2.2) | Weekly breakdown; team answer |
| Deployed system, test execution results, test reports, usability test results | Weeks 8–9 | Weekly breakdown |
| Completed, optimized, error-free deployed system | Week 10 | Weekly breakdown |
| Proof of usage and payments; usage analytics report | Weeks 11–12 | Weekly breakdown |
| Full research paper draft | Weeks 13–14 | Weekly breakdown |
| Business model canvas; pitch deck | Week 15 | Weekly breakdown |
| Final manuscript; deployed system demo | Weeks 16–17 | Weekly breakdown |
| Final revisions; endorsement for incubation, publication, or scaling | Week 18 | Weekly breakdown |
| Source code repository (GitHub: SherieHub/CeView) | Continuous | Repository |

[Table 1.1.3] Project Deliverables

### 1.1.4.  Schedule and budget summary

Week dates are derived from the course submission dates, assuming Sunday–Saturday weeks with Week 1 = 16–22 Aug 2026. [confirm]

| Milestone / Phase | Weeks | Dates (2026) |
| --- | --- | --- |
| MVP Validation & Planning | 1–2 (breakdown); submission Week 4 | Aug 16 – Aug 29; report due Sep 12 |
| Requirements & Design Refactoring | 3 (breakdown); submission Week 5 | Aug 30 – Sep 5; SRS/SPMP/SDD due Sep 19 |
| STD submission | 6 | Sep 26 |
| Full System Implementation (course phase) | 4–7 | Sep 6 – Oct 3 |
| ph3-dev implementation: Lead Ads setup, attribution | 6–9 | Sep 20 – Oct 17 |
| Deployment & System Testing | 8–9 | Oct 4 – Oct 17 |
| System Enhancement & Iteration | 10 | Oct 18 – Oct 24 |
| Actual Usage & Evidence Collection | 11–12 | Oct 25 – Nov 7 |
| Research Writing & Analysis | 13–14 | Nov 8 – Nov 21 |
| Commercialization & Sustainability Planning | 15 | Nov 22 – Nov 28 |
| Final Defense & Demo | 16–17 | Nov 29 – Dec 12 [exact defense date] |
| Revisions & Endorsement | 18 | Dec 13 – Dec 19 |

[Table 1.1.4] Schedule Summary

Schedule overlaps to manage. First, the STD is due in Week 6, while the breakdown places test planning in Weeks 8–9. The STD (plan and cases) will be submitted in Week 6, and test execution and reports follow in Weeks 8–9. Second, ph3-dev implementation (Weeks 6–9) overlaps Deployment & System Testing (Weeks 8–9). [confirm how testing of ph3 features is sequenced]

Budget summary. Paid cost items: SerpApi, AWS hosting, and Hugging Face model hosting. Groq is used on its free tier (Project team (answers of 19 Sep 2026)). Amounts and funding source: [placeholder]. See 5.2.4.

## 1.2.  Evolution of plan

This plan is labelled Beta Testing (Project team (answers of 19 Sep 2026)). It will be updated when scope, schedule, or budget changes, and at the phase gates listed below. Updates are version-controlled with the project documents in [location, e.g., repository docs/ folder or shared drive] and communicated to the team through [Jira / team channel].

| Version | Primary Author(s) | Description of Version | Date Expected |
| --- | --- | --- | --- |
| Beta | [author(s)] | Refactored SPMP for Semester 2 beta testing; built from repository evidence (ph2-dev @ 5116a161) and team answers | Sep 19, 2026 |
| Beta rev. 1 | [author(s)] | Revised after adviser/SME review; placeholders resolved | [date] |
| Post-testing | [author(s)] | Updated after Deployment & System Testing (Weeks 8–9) | [date] |
| Final | [author(s)] | Final version accompanying the final manuscript | [date] |

[Table 1.2] Evolution Plan

# 2.  References

[Reference list to be supplied by the team.] (Project team (answers of 19 Sep 2026): placeholder for now)

Candidate entries, pending team confirmation:

- [1] IEEE Std 1058-1998, IEEE Standard for Software Project Management Plans (basis of the CIT-U SPMP template).

- [2] CeView Software Requirements Specification (Refactored), [version, date].

- [3] CeView Software Design Description (Refactored), [version, date].

- [4] CeView Software Test Document, [version, date].

# 3.  Definitions

| Term | Definition |
| --- | --- |
| BiLSTM | Bidirectional Long Short-Term Memory neural network; combined with a Transformer in CeView's hosted demand-prediction model |
| CI | Continuous Integration (GitHub Actions workflows in .github/workflows) |
| CVW-## | Jira ticket key used in CeView branch names |
| AWS | Amazon Web Services (production hosting; see 6.3) |
| CAC / CPC / CTR | Customer Acquisition Cost / Cost Per Click / Click-Through Rate (Module 4 metrics) |
| DSR | Design Science Research (validation framework) |
| ECR / ECS / RDS | Amazon Elastic Container Registry / Elastic Container Service / Relational Database Service |
| HF | Hugging Face (model hosting via Hugging Face Spaces) |
| JWT | JSON Web Token (API authentication) |
| Lead Ads | Meta advertising format that collects lead information from users |
| MSME | Micro, Small, and Medium Enterprise |
| MVP | Minimum Viable Product |
| PES | Promotional Effectiveness Score (Module 4.2) |
| pgvector | PostgreSQL extension for vector similarity search |
| SBERT | Sentence-BERT (business classification, Module 1) |
| SDD | Software Design Description |
| SME | Subject Matter Expert |
| SPMP | Software Project Management Plan |
| SRS | Software Requirements Specification |
| SUS | System Usability Scale (usability questionnaire) |
| TCT | Task Completion Time (timed task trials) |
| UAT | User Acceptance Testing |
| STD | Software Test Document |
| W&B | Weights & Biases (model experiment tracking) |

[Table 3] Definitions

# 4.  Project organization

## 4.1.  External structure

The project is conducted under the College of Computer Studies, Cebu Institute of Technology – University. External entities that interact with the project:

| Entity | Relationship to project | Details |
| --- | --- | --- |
| Course adviser / instructor | Sets deliverables and deadlines; gives feedback (Weeks 8–9) | [name] |
| Defense panel | Technical, research, and commercial defense (Weeks 16–17) | [names] |
| Subject Matter Expert(s) | Review project work products | [name(s), area of expertise] |
| Pilot MSMEs | Validation, usability and acceptance testing; paying customers | [number and names] |
| Third-party service providers | Meta (Marketing API), Amazon Web Services (hosting), Hugging Face, SerpApi, Groq (free tier), W&B | See 5.1.3 |

[Table 4.1] External Interfaces

[Organization diagram to be inserted]

## 4.2.  Internal structure

The team works as a Scrum team inside a hybrid process (see 6.1). Work is tracked in Jira, and daily coordination happens through daily stand-ups (Project team (answers of 19 Sep 2026)). Supporting processes (configuration management, quality assurance, and verification & validation) are carried out by team members; responsibilities are in Table 4.3.1.

[Internal organization chart: lines of authority, e.g., Product Owner → Scrum Master → Development Team]

## 4.3.  Roles and responsibilities

| Team Member | Role & Responsibilities — SEM 1 | Role & Responsibilities — SEM 2 |
| --- | --- | --- |
| [Member 1] | [role] | [role] |
| [Member 2] | [role] | [role] |
| [Member 3] | [role] | [role] |
| [Member 4] | [role] | [role] |
| [Member 5] | [role] | [role] |

[Table 4.3.1] Role and Responsibilities

| Scrum role | Assigned to |
| --- | --- |
| Product Owner | [name] |
| Scrum Master | [name] |
| Development Team | [names] |

[Table 4.3.2] Scrum Role Assignment

# 5.  Managerial process plans

## 5.1.  Start-up plan

### 5.1.1.  Estimation plan

Semester 2 phases and deadlines are fixed by the course schedule (1.1.4). Within implementation, work is broken down into Jira tickets (CVW-##) and planned in Scrum sprints (Project team (answers of 19 Sep 2026); branch names such as CVW-35-forecasting-model-integration).

- Estimation method (e.g., story points, planning poker, ideal hours): [placeholder]

- Sprint length: [placeholder]

- Re-estimation trigger and frequency, e.g., at sprint planning and when a course deadline is at risk: [placeholder]

- Cost estimation for paid services, based on provider pricing and expected usage: [placeholder]

### 5.1.2.  Staffing plan

| Name | Affiliation to project | SEM 1 | SEM 2 |
| --- | --- | --- | --- |
| [Member 1] | Student / Team member | [availability] | [availability] |
| [Member 2] | Student / Team member | [availability] | [availability] |
| [Member 3] | Student / Team member | [availability] | [availability] |
| [Member 4] | Student / Team member | [availability] | [availability] |
| [Member 5] | Student / Team member | [availability] | [availability] |
| [Adviser] | Adviser | [availability] | [availability] |
| [SME] | Subject Matter Expert | [availability] | [availability] |

[Table 5.1.2] Staff Plan

### 5.1.3.  Resource acquisition plan

Non-personnel resources in use or required. The evidence column shows where each resource appears in the repository. Responsibility and timing are placeholders.

| Resource | Purpose | Evidence | Cost type | Responsible / when |
| --- | --- | --- | --- | --- |
| GitHub repository & Actions | Source control, pull requests, CI | Repository; .github/workflows | [confirm] | [ ] |
| Jira | Backlog, sprints, ticket tracking | Team answer; CVW-## keys | [confirm] | [ ] |
| AWS hosting (application + PostgreSQL) | Deployed system (see 6.3) | Team answer; replaces render.yaml (Render) | Paid (team) | [account owner]; set up before Weeks 8–9 deployment |
| Hugging Face Space | Hosted BiLSTM + Transformer demand model | bilstm_forecaster.py:37 | Paid (team) | [ ] |
| SerpApi | Search-trend data for Module 2 ingestion | Team answer; trend_service | Paid (team) | [ ] |
| Groq API | LLM for content generation and reports | README.md; GROQ_API_KEY | Free tier (team) | [ ] |
| Weights & Biases | Model telemetry | Commit 21424c7b | [free / paid] | [ ] |
| Meta developer app + Marketing API | Ad metrics (current); Lead Ads campaign creation (ph3) | AD_PLATFORM_SETUP.md; team answer (app approval done) | [ ] | [ ] |
| Payment provider | Collecting customer payments | Team answer | [ ] | [provider TBD] |

[Table 5.1.3] Resource Acquisition

### 5.1.4.  Project staff training plan

[Training plan to be supplied: training types, participants, entry/exit criteria, method.]

Knowledge areas implied by the Semester 2 scope, listed as candidates for the team to confirm: Meta Marketing API (Lead Ads campaign creation); marketing attribution design; payment-provider integration; usability and acceptance test facilitation with pilot MSMEs.

## 5.2.  Work plan

### 5.2.1.  Work activities

The work breakdown structure below is built from the course weekly breakdown and the confirmed Semester 2 scope. Detailed tasks are kept as Jira tickets.

| WBS | Work activity | Work products | Weeks | Depends on |
| --- | --- | --- | --- | --- |
| 1.0 | MVP Validation & Planning: review Semester 1 MVP; user and customer validation; refine scope and success metrics | MVP Validation Report; updated SPMP | 1–4 | — |
| 2.0 | Requirements & Design Refactoring: update requirements from validation; refactor design; update traceability matrix | Refactored SRS, SDD, SPMP; traceability matrix | 3–5 | 1.0 |
| 3.0 | Full System Implementation | Feature-complete system; implementation reports | 4–9 | 2.0 |
| 3.1 | Content Studio → Meta Lead Ads campaign setup (ph3-dev); ads only | Feature on ph3-dev | 6–9 | 2.0 |
| 3.2 | Marketing attribution (per spec 2026-09-14), across Modules 2, 3 and 4 | Feature on ph3-dev | 6–9 | 2.0 |
| 3.3 | Payment capability and free/paid tiers | Payment feature; pricing [TBD] | [weeks] | 2.0 |
| 3.4 | Production forecasting setup: FORECAST_ENGINE=bilstm with the HF-hosted model | Configured deployment | [weeks] | — |
| 3.5 | Performance, security, and scalability improvements | Implementation reports | 4–7 | — |
| 3.6 | AWS environment and deployment pipeline setup (replaces Render; see 6.3) | AWS environment; GitHub Actions deploy workflow | [weeks — before 8–9] | — |
| 4.0 | Deployment & System Testing: test planning and case design; STD; production or pilot deployment; functional, integration, system, and acceptance testing; adviser and user feedback | STD (Week 6); deployed system; test execution results; usability test results | 6, 8–9 | 3.0 |
| 5.0 | System Enhancement & Iteration: feature refinement; bug fixing and optimization; actual-usage preparation | Completed, optimized, error-free deployed system | 10 | 4.0 |
| 6.0 | Actual Usage & Evidence Collection: onboard paying customer(s); usage monitoring and analytics; transaction and payment evidence | Proof of usage and payments; usage analytics report | 11–12 | 5.0, 3.3 |
| 7.0 | Research Writing & Analysis: data analysis; results and discussion; paper refinement | Full research paper draft | 13–14 | 6.0 |
| 8.0 | Commercialization & Sustainability Planning: Lean Canvas; market and competitor analysis; pricing and adoption strategy | Business model canvas; pitch deck | 15 | 6.0 |
| 9.0 | Final Defense & Demo: technical, research, and commercial defense; live demo | Final manuscript; deployed system demo | 16–17 | 7.0, 8.0 |
| 10.0 | Revisions & Endorsement | Final revisions; endorsement | 18 | 9.0 |
| PM | Project management: daily stand-ups, sprint events, Jira tracking, SPMP upkeep | Jira board; updated SPMP | 1–18 | — |

[Table 5.2.1] Work Breakdown Structure

Acceptance criteria per work product: [placeholder]

### 5.2.2.  Schedule allocation

Phase timing follows the course weekly breakdown, and document due dates follow the submission table (Project team (answers of 19 Sep 2026)). Week-to-date mapping (Sunday–Saturday, derived; [confirm]):

| Week | Dates | Planned activity | Fixed deadline |
| --- | --- | --- | --- |
| 1–2 | Aug 16 – Aug 29 | MVP Validation & Planning |  |
| 3 | Aug 30 – Sep 5 | Requirements & Design Refactoring |  |
| 4 | Sep 6 – Sep 12 | Implementation begins | MVP Validation — Sep 12 |
| 5 | Sep 13 – Sep 19 | Implementation | SRS, SPMP, SDD — Sep 19 |
| 6 | Sep 20 – Sep 26 | Implementation; ph3-dev starts | STD — Sep 26 |
| 7 | Sep 27 – Oct 3 | Implementation (ph3-dev) | [course deadline] |
| 8–9 | Oct 4 – Oct 17 | Deployment & System Testing; ph3-dev completes | [ ] |
| 10 | Oct 18 – Oct 24 | Enhancement & Iteration | [ ] |
| 11–12 | Oct 25 – Nov 7 | Actual Usage & Evidence | [ ] |
| 13–14 | Nov 8 – Nov 21 | Research Writing | [ ] |
| 15 | Nov 22 – Nov 28 | Commercialization | [ ] |
| 16–17 | Nov 29 – Dec 12 | Final Defense & Demo | [defense date] |
| 18 | Dec 13 – Dec 19 | Revisions & Endorsement | [ ] |

[Table 5.2.2] Schedule Allocation

Critical path (proposed, pending team review): 3.1/3.2 ph3-dev features → 4.0 system testing → 5.0 enhancement → 6.0 paying-customer evidence → 7.0 research paper → 9.0 defense. The paying-customer evidence in Weeks 11–12 also depends on 3.3 payment capability, whose schedule is [TBD].

### 5.2.3.  Resource allocation

| WBS | Personnel | Computing / services |
| --- | --- | --- |
| 1.0–2.0 | [names] | Documentation tools [ ] |
| 3.1 | [names] | Meta developer app, Marketing API, test ad account [ ] |
| 3.2 | [names] | PostgreSQL, Spring Boot, fastapi-sbert (captions) |
| 3.3 | [names] | Payment provider [ ] |
| 3.4 | [names] | Hugging Face Space, SerpApi, AWS |
| 3.6 | [names] | AWS (ECS/EC2, RDS, S3, CloudFront, ECR, Parameter Store), GitHub Actions |
| 4.0–6.0 | [names] | Hosting, CI, Playwright; pilot MSMEs |
| 7.0–10.0 | [names] | [ ] |

[Table 5.2.3] Resource Allocation

Hours per member per week: [placeholder]

### 5.2.4.  Budget allocation

| Cost item | WBS | Estimated cost | Period | Funded by |
| --- | --- | --- | --- | --- |
| SerpApi subscription | 3.4, 6.0 | [₱ / $] | [ ] | [ ] |
| AWS hosting (compute, RDS, S3/CloudFront) | 3.6, 4.0–9.0 | [ ] | [ ] | [ ] |
| Hugging Face model hosting | 3.4–9.0 | [ ] | [ ] | [ ] |
| Groq / LLM usage | 3.0–9.0 | ₱0 (free tier) | — | — |
| Meta ad spend for Lead Ads tests | 3.1, 4.0 | [ ] | [ ] | [team or pilot MSME] |
| Payment provider fees | 6.0 | [ ] | [ ] | [ ] |
| Other (printing, transport for pilot visits) | — | [ ] | [ ] | [ ] |
| Total |  | [ ] |  |  |

[Table 5.2.4] Budget Allocation

## 5.3.  Control plan

The controls below combine the confirmed process elements (Jira, daily stand-ups, Scrum, fixed course gates) with evidence of existing engineering controls in the repository.

### 5.3.1.  Requirements control plan

- The Refactored SRS is the requirements baseline. The traceability matrix links requirements to design, code, and tests (WBS 2.0).

- Requirement changes are raised as Jira tickets. Larger features follow the repository's existing design-spec → implementation-plan practice (docs/superpowers/specs, docs/superpowers/plans) (e.g., 2026-09-14-marketing-attribution-design.md, 2026-09-11-bilstm-transformer-integration.md).

- Scope change approval authority / change control board: [placeholder]

- Impact assessment of changes on schedule, budget, and risk: [procedure placeholder]

### 5.3.2.  Schedule control plan

- Progress is tracked in Jira and reviewed at daily stand-ups (Project team (answers of 19 Sep 2026)).

- Milestones are judged achieved when the course deliverable is submitted and accepted by [adviser].

- Corrective action when behind schedule: [e.g., re-prioritize backlog, re-scope, escalate to adviser]

### 5.3.3.  Budget control plan

- Paid-service usage (SerpApi, AWS, and Hugging Face hosting) is tracked against Table 5.2.4 at [frequency] by [owner]. Groq free-tier usage is monitored against its rate limits. An AWS Budgets alert is set at [amount].

- Action when spend exceeds budget: [e.g., downgrade tier, cap usage, switch to free tier]. CeView's product design already includes a free tier (Project team (answers of 19 Sep 2026)).

### 5.3.4.  Quality control plan

- Automated tests exist at four levels (repository, ph2-dev): 84 Vitest frontend test files; 66 JUnit test classes; pytest suites (18 test files in fastapi-sbert, 11 in fastapi-transformer); and 12 Playwright end-to-end spec files.

- GitHub Actions run these suites on push and pull request (.github/workflows/*.yml). Gap: workflow triggers currently list main, task_allocation, and ph1-dev only. The baseline ph2-dev and the planned ph3-dev are not covered. [team decision: extend CI triggers?]

- Code enters phase branches through pull requests (PRs #20–#36 merged into ph1-dev/ph2-dev) (merge commits). PR review and approval rule: [placeholder]

- SME review of work products (Project team (answers of 19 Sep 2026)): [which products, when]

### 5.3.5.  Reporting plan

| Report / forum | Audience | Frequency | Medium |
| --- | --- | --- | --- |
| Daily stand-up | Team | Daily | Jira / [in person or online] |
| Sprint review | Team, [adviser/SME] | [per sprint] | [ ] |
| Adviser consultation | Adviser | [ ] | [ ] |
| Course deliverable submissions | Adviser / course | Per 1.1.3 | [LMS] |
| Adviser and user feedback session | Adviser, pilot MSMEs | Weeks 8–9 | [ ] |

[Table 5.3.5] Reporting Plan

### 5.3.6.  Metrics collection plan

- Process metrics from Jira (e.g., velocity, burndown, ticket cycle time): [which are used]

- Test metrics: CI pass/fail per workflow; test execution results (Weeks 8–9).

- Model telemetry: forecasting runs logged to Weights & Biases (commit 21424c7b).

- Product metrics: usability test results (Weeks 8–9); usage analytics and payment evidence (Weeks 11–12); success metrics from MVP validation [ ].

### 5.3.7.  Risk management plan

Risk process (identification cadence, owner, scoring scale, review forum): [placeholder]. The register below lists risks visible in repository evidence or the confirmed schedule. It is a proposal pending team review (Project team (answers of 19 Sep 2026): "to be reviewed").

| # | Proposed risk | Evidence | Proposed response |
| --- | --- | --- | --- |
| R1 | ph3-dev implementation (Weeks 6–9) overlaps system testing (Weeks 8–9); ph3 features may reach testing late | Tables 1.1.4, 5.2.2 | Test ph3 features incrementally; [ ] |
| R2 | Paying-customer evidence (Weeks 11–12) depends on a payment capability with no schedule or pricing yet | WBS 3.3 | Schedule 3.3 explicitly; [ ] |
| R3 | Hosted forecasting model unavailable or slow (external HF Space); forecasts fail by design instead of padding | bilstm_forecaster.py:19, 88–95 | [ ] |
| R4 | Paid API costs exceed budget | Team answer; Table 5.2.4 | Budget control (5.3.3) |
| R5 | CI does not run on the baseline branch; regressions may go undetected | .github/workflows triggers | Extend triggers [decision] |
| R6 | Stale documentation: README/CLAUDE.md still describe forecasting as "XGBoost + Groq/Gemini" | README.md; .claude/CLAUDE.md | Update docs |
| R7 | Repository hygiene: 142 committed __pycache__ files, committed e2e/node_modules, stray file backend/fastapi-sbert/cd | git ls-tree ph2-dev | Clean up and extend .gitignore |
| R8 | Known Module 2 defects from the 10 Sep audit may remain open | MODULE_2_E2E_STATUS_AND_DATA_MAPPING.md | [TBD — status review] |
| R9 | AWS migration: no AWS deployment configuration exists yet, and it must be ready before the Weeks 8–9 deployment | render.yaml is the only deploy config in the repo; team hosting preference | Schedule WBS 3.6 early; [ ] |
| R10 | Groq free-tier rate or usage limits may throttle content generation during pilot usage (Weeks 8–12) | Team answer (Groq on free tier) | Monitor limits; [fallback: paid tier or alternate model] |

[Table 5.3.7] Proposed Risk Register (pending team review)

### 5.3.8.  Project closeout plan

- Week 18: final revisions and endorsement for incubation, publication, or scaling (course weekly breakdown).

- Archiving: final code state tagged in GitHub [tag/branch naming]; documents archived at [location].

- Post-mortem / lessons learned: [placeholder]

- Handover of paid-service accounts, API keys, and pilot-customer commitments after the course: [placeholder]

# 6.  Technical process plans

## 6.1.  Process Model

CeView uses a hybrid process model (Project team (answers of 19 Sep 2026)):

- Waterfall at the course level. The semester moves through sequential phases with document gates: MVP validation → requirements and design refactoring (SRS, SDD, SPMP) → implementation → deployment and testing (STD) → enhancement → actual usage → research → commercialization → defense → endorsement.

- Scrum within implementation. Work runs in 1-week sprints, Sunday–Saturday, matching the course's weekly deliverable deadlines (Saturdays, 11:59 PM) (course submission table). Each sprint includes:

  - Sprint planning at the start of each week: select Jira tickets and tie them to that week's course deliverable.

  - Daily stand-up, held [in person / online / written in Jira] (Project team (answers of 19 Sep 2026)).

  - Sprint review at the end of the week: demo completed tickets to the team and, when available, the advisers or Subject Matter Expert.

  - Sprint retrospective after the review; its findings feed 7.8 Process Improvement.

This continues the Scrum methodology set out in Semester 1, where each sprint covered one of CeView's five phases (Software Project Proposal, Part 3: Development Methodology).

- Kanban in Jira. Tickets (CVW-##) move across the board columns To Do → In Progress → In Review → Done. "In Review" means a pull request is open against the phase branch; "Done" means the pull request is merged and tests pass. Work-in-progress limit: no more than 2 In Progress tickets per member.

Engineering flow observed in the repository. A Jira ticket becomes a feature branch named after the ticket (e.g., CVW-33-meta-and-tik-tok-ads-connection-testing). Larger items get a design spec and implementation plan in docs/superpowers. Work merges by pull request into the phase branch (ph1-dev → ph2-dev → ph3-dev) (branch list; merge commits).

Process model diagram. A top row shows the course's Waterfall phase gates (Weeks 1–18). The implementation phase (Weeks 4–10) expands into a repeating weekly Scrum loop: Jira backlog → sprint planning → build on a ticket branch → pull request and automated tests → merge into ph3-dev → sprint review → retrospective. Each gate points to its course deliverable (SRS/SDD/SPMP, STD, deployed system, final manuscript). [Insert figure]

## 6.2.  Methods, tools, and techniques

| Category | Tools / methods | Source |
| --- | --- | --- |
| Frontend | React 19, TypeScript, Vite, Tailwind | README.md |
| Orchestration API | Spring Boot 3.3, Java 21, JWT authentication | README.md |
| AI services | FastAPI (Python 3.12): fastapi-sbert (SBERT classification, LangGraph content generation, Groq — free tier); fastapi-transformer (forecast engine registry) | README.md; forecast_engine.py; team answer |
| Forecasting model | BiLSTM + Transformer on Hugging Face Spaces, called by the "bilstm" engine | Team answer; bilstm_forecaster.py |
| Database | PostgreSQL 16 + pgvector; Flyway migrations (V1–V42) | README.md; db/migration |
| External data / APIs | SerpApi; Meta Marketing API; TikTok Ads API (metrics only) | Team answer; AD_PLATFORM_SETUP.md |
| Testing | Vitest, JUnit, pytest, Playwright | README.md |
| CI / deployment | GitHub Actions for tests; Docker images deployed to Amazon Web Services (AWS). The Render blueprint (render.yaml) is replaced by AWS. | Team answer (hosting preference); .github/workflows |
| Configuration management | Git, GitHub, pull requests | Repository |
| Project planning & tracking | Jira (Scrum sprints, Kanban board) | Team answer |
| Model telemetry | Weights & Biases | Commit 21424c7b |
| AI-assisted development | Repository guidance for Claude Code, Codex, Gemini, Copilot (AGENTS.md as canonical rules) | AGENTS.md; .github/copilot-instructions.md |
| Documentation | Google Docs for project documents (SRS, SDD, SPMP); draw.io for design diagrams; Markdown and PlantUML/Mermaid in docs/ | Google Drive (CeView_SRS Final, 2526-sem2-cs342-10_SDD, CeView_SPMP_Beta, CeView SDD.drawio); docs/ |
| Validation methods | Design Science Research framework: technical feasibility testing, user acceptance testing with MSME operators, and expert review of generated content | Software Project Proposal, Part 3: Validation Approach |

[Table 6.2] Methods, Tools, and Techniques

Technical standards: repository rules in AGENTS.md apply. Changes stay within module boundaries, multi-tenant isolation is preserved, and relevant tests are run after changes (AGENTS.md). API contracts are defined in backend/CONTRACT.md.

## 6.3.  Infrastructure Plan

- Local development: Docker Compose stack (backend/docker-compose.yml) or native/H2 path, with environment variables from .env.example files (README.md; RUNNING.md).

- Hosting: Amazon Web Services (AWS), the team's preferred host (Project team (answers of 19 Sep 2026)). It replaces the Render setup declared in render.yaml. Each CeView component maps to an AWS service as follows:

| CeView component | AWS service |
| --- | --- |
| Frontend (static Vite build) | Amazon S3 + CloudFront |
| Spring Boot API | Amazon ECS on Fargate (container), behind an Application Load Balancer |
| fastapi-sbert, fastapi-transformer | Amazon ECS on Fargate (one service each) |
| PostgreSQL 16 + pgvector | Amazon RDS for PostgreSQL 16 with the pgvector extension enabled |
| Container images | Amazon ECR |
| Logs and health checks | Amazon CloudWatch, using the existing /actuator/health and /healthz endpoints (render.yaml) |

[Table 6.3.1] AWS Hosting Components

Lower-cost alternative: run the existing backend/docker-compose.yml on a single Amazon EC2 instance, with the frontend on S3 + CloudFront. This suits a pilot-scale beta at lower cost but scales less. Team choice: [ECS Fargate / single EC2]. AWS region: [e.g., ap-southeast-1 Singapore]. Account owner / billing: [placeholder].

The BiLSTM + Transformer model stays hosted on Hugging Face Spaces; the forecasting service calls it from AWS (bilstm_forecaster.py:37).

- Production forecasting configuration: set FORECAST_ENGINE=bilstm, HF_DEMAND_SPACE and HF_TOKEN in the forecasting service's AWS task definition. The engine defaults to "stub" otherwise (docker-compose.yml:65; bilstm_forecaster.py:37–39).

- Secrets management: API keys and credentials (Groq, SerpApi, Hugging Face, Meta, JWT secret, database credentials, payment provider) are stored encrypted in AWS Systems Manager Parameter Store (or AWS Secrets Manager) and injected into the containers at start-up. Nothing is committed to the repository; only .env.example templates stay in git (backend/, frontend/ .env.example).

- Deployment pipeline: a GitHub Actions workflow builds the images, pushes them to ECR, and deploys to AWS on merge into the release branch. This also closes the current gap where CI does not run on ph2-dev/ph3-dev (see 5.3.4). Release branch: [placeholder].

- Team workstations and facilities: team members' own laptops with Docker Desktop, JDK 21, Python 3.12, and Node.js (README.md prerequisites). CIT-U facilities for meetings and defense: [placeholder].

## 6.3.  Product Acceptance Plan

The product is accepted by pilot MSMEs through validation, usability, and acceptance testing (Project team (answers of 19 Sep 2026)), run during Deployment & System Testing (Weeks 8–9). Pilot partners are being sourced through requests to DOT Region VII, DTI, and DICT (CeView Letter of Participation, 16 Sep 2026). The measurable targets below come from the Semester 1 proposal and apply unless the MVP Validation Report revised them [confirm against MVP Validation Report]. The PES target of 80% or higher remains in force (Project team (answers of 19 Sep 2026)).

| Acceptance activity | Method | Criteria | Participants |
| --- | --- | --- | --- |
| Validation test | Timed task trials: marketing preparation time with vs. without CeView (Proposal, Objective 1) | Preparation time reduced by at least 40% | Pilot MSMEs [count] |
| Usability test | System Usability Scale (SUS) questionnaire after scripted tasks (Proposal, Research Question 5; Bangor et al., 2008) | SUS score of 68 or higher (published average, Bangor et al.) | Pilot MSMEs |
| Acceptance test | Test cases from the Software Test Document (due Sep 26) | All critical/high test cases pass; no open critical defects | Pilot MSMEs; advisers J. V. Serato and R. P. Laviste (Letter of Participation) |
| Model and output quality | Benchmarks from the proposal's specific objectives | Forecast MAPE ≤ 15%; classification accuracy ≥ 85%; PES ≥ 80%; content-generation response ≤ 8 seconds (set in Semester 1 for Gemini; now measured on the Groq free-tier generator) (Proposal, Objectives 1.5, 2, 2.16, 3; Validation Approach) | Team; Subject Matter Expert |
| Expert evaluation | Social media marketing specialists review the quality and cultural fit of generated content (Proposal, Validation Approach) | [rating scale and pass mark] | SME [name] |
| Live demonstration | Demo at final defense (Weeks 16–17) | Panel judgment | Defense panel |

[Table 6.3.2] Product Acceptance

Formal sign-off. Each pilot MSME signs a one-page acceptance form after its user acceptance testing session, recording the tasks completed, the SUS score, and any open issues. The advisers countersign the consolidated acceptance summary, which is filed with the test reports. Form owner: [placeholder].

# 7.  Supporting process plans

## 7.1.  Configuration management plan

- Tooling: Git + GitHub (SherieHub/CeView).

- Baselines: ph2-dev is the current baseline (commit 5116a161, 14 Sep 2026). main is stale (last updated 10 Aug 2026; 140 commits behind ph2-dev) (Project team (answers of 19 Sep 2026); git history). Semester 2 feature work continues on ph3-dev, branched from ph2-dev [confirm].

- Change units: one feature branch per Jira ticket, merged by pull request. Database changes are versioned Flyway migrations.

- Configuration items: source code, Flyway migrations, CI workflows, AWS deployment configuration and GitHub Actions deploy workflow (replacing render.yaml), environment templates (.env.example), and project documents.

- Release management: promotion of ph3-dev to a release/demo baseline and the role of main: [placeholder]

- Open issue: CI triggers do not include ph2-dev or ph3-dev (see 5.3.4).

## 7.2.  Verification and validation plan

| Level | Technique / tool | Current evidence | When |
| --- | --- | --- | --- |
| Unit / component | Vitest, JUnit, pytest | 84 / 66 / 29 test files on ph2-dev | Continuous (Weeks 4–10) |
| Integration | JUnit against H2; Vitest integration; service contract tests | frontend/tests/integration; frontend/tests/contract | Continuous; Weeks 8–9 |
| System / end-to-end | Playwright against Dockerized backend | e2e/tests (12 specs); nightly e2e workflow | Weeks 8–9 |
| Acceptance / usability | Pilot MSME tests (see 6.3 Product Acceptance) | — | Weeks 8–9 |
| Model validation | Forecast validation; W&B telemetry | Commit 21424c7b | [ ] |
| Verification reviews | PR review; SME review; traceability matrix | Merge commits | Continuous |

[Table 7.2] V&V Plan

Test planning details are in the Software Test Document (due Sep 26, 2026). V&V independence (who tests vs. who develops): [placeholder].

## 7.3.  Documentation plan

| Document | Due | Prepared by | Reviewed by |
| --- | --- | --- | --- |
| MVP Validation Report | Sep 12, 2026 | [ ] | [ ] |
| Refactored SRS | Sep 19, 2026 | [ ] | [ ] |
| Refactored SPMP (this document) | Sep 19, 2026 | [ ] | [ ] |
| Refactored SDD | Sep 19, 2026 | [ ] | [ ] |
| Traceability matrix | [ ] | [ ] | [ ] |
| Software Test Document | Sep 26, 2026 | [ ] | [ ] |
| Implementation reports | Weeks 4–7 | [ ] | [ ] |
| Test execution & usability results | Weeks 8–9 | [ ] | [ ] |
| Usage analytics report | Weeks 11–12 | [ ] | [ ] |
| Research paper draft | Weeks 13–14 | [ ] | [ ] |
| Business model canvas; pitch deck | Week 15 | [ ] | [ ] |
| Final manuscript | Weeks 16–17 | [ ] | [ ] |

[Table 7.3] Documentation Plan

Technical documentation maintained in the repository alongside code: README.md, RUNNING.md, ARCHITECTURE.md, ARCHITECTURE_SPEC.md, backend/CONTRACT.md, docs/module-1..4, and design specs and plans in docs/superpowers. README.md and .claude/CLAUDE.md need updating to describe the BiLSTM + Transformer forecasting engine (see R6).

## 7.4.  Quality assurance plan

QA combines automated tests in CI (5.3.4), pull-request review, SME review, and the V&V activities in 7.2. QA owner, audit checklist, and process-compliance checks: [placeholder].

## 7.5.  Reviews and audits

| Review | Conducted by | When |
| --- | --- | --- |
| Developer peer review (pull requests) | [reviewers / approval rule] | Every merge |
| Subject Matter Expert review | [SME name(s)] | [schedule] |
| Adviser review of deliverables | [adviser] | At each submission; feedback in Weeks 8–9 |
| Pilot MSME review (acceptance) | Pilot MSMEs | Weeks 8–9 |
| Final defense (technical, research, commercial) | Defense panel | Weeks 16–17 |

[Table 7.5] Reviews and Audits

External bodies that approve or regulate the product: Meta platform review for Marketing API permissions (completed per team) (Project team (answers of 19 Sep 2026)). Others: [e.g., data privacy requirements].

## 7.6.  Problem resolution plan

- Defects and problems are logged as Jira tickets (CVW-##), prioritized in [stand-up / sprint planning], fixed on a ticket branch, and closed after PR merge and passing tests.

- Severity/priority scheme and rework tracking: [placeholder]

- Status of issues from the Module 2 E2E audit (10 Sep 2026): [TBD] (docs/module-2/MODULE_2_E2E_STATUS_AND_DATA_MAPPING.md)

## 7.7.  Subcontractor management plan

[Pending team review.] (Project team (answers of 19 Sep 2026)) No subcontracted development was found in the repository. The project depends on third-party service providers (Table 5.1.3). Whether these are managed under this subclause is to be decided.

## 7.8.  Process improvement plan

[Placeholder: e.g., sprint retrospectives, end-of-phase lessons learned, root-cause analysis of recurring defects.]

# 8.  Additional Plans

- Security & privacy: all API routes are JWT-gated and data is isolated per business operator (README.md "Current State"). Ad-platform connections use OAuth, with per-operator scoping of stored connections (AdConnectionController.java; AdPlatformConnectionRepository.java). Handling of customer payment data and lead data collected through Meta Lead Ads: [placeholder].

- User onboarding / training: a first-login tutorial modal exists for new users (commit 5e1d7450). Pilot MSME onboarding plan: [placeholder].

- Product installation / deployment plan: production or pilot deployment on AWS in Weeks 8–9 (see 6.3).

- Maintenance and support after the course (incubation or scaling path): [placeholder].

# 9.  Plan Annexes

### Annex A. Repository evidence summary (ph2-dev @ 5116a161)

- Recent completed work: Module 1 uniqueness-score cohort statistics and calibration (PRs #29–#31); Meta/TikTok ad connections, campaign selection, live week-to-date ad metrics (PRs #34–#35; commits 4803aacb, 5116a161); Module 2 end-to-end completion and BiLSTM + Transformer integration (PR #36; commit 4c97928a).

- Approved design awaiting implementation: marketing attribution (spec dated 2026-09-14).

- Git author identities on ph2-dev: austi, SherieHub, Jamjamzz, AustineLomocso, Luis, ctrlneenja, Austine, Christian Luis C. Fernandez, Janeen Gabrielle. Mapping to team members: [placeholder].

### Annex B. Assumptions & Open Questions

| # | Open item | Affects |
| --- | --- | --- |
| 1 | Team names, roles (SEM 1/SEM 2), Scrum role assignment, adviser, SME, panel | 4, 5.1.2, 5.2.3 |
| 2 | Semester start date (derived as Aug 16, 2026) and week boundaries | 1.1.4, 5.2.2 |
| 3 | ph3-dev (Weeks 6–9) overlaps system testing (Weeks 8–9): sequencing of ph3 feature testing | 1.1.4, 5.2.2, 7.2 |
| 4 | Schedule and branch for the payment capability (WBS 3.3); pricing; payment provider | 1.1.1, 5.2.1, 8 |
| 5 | Budget amounts and funding source; whether W&B is paid | 1.1.4, 5.2.4 |
| 6 | AWS setup: ECS Fargate vs. single EC2, region, account owner, release branch | 5.1.3, 6.3 |
| 7 | Sprint length, estimation method, ceremonies, Jira board setup | 5.1.1, 6.1 |
| 8 | Scope-change approval authority | 5.3.1 |
| 9 | Pilot MSME count; acceptance and usability criteria; sign-off | 6.3 (Product Acceptance) |
| 10 | Whether CI triggers are extended to ph2-dev/ph3-dev | 5.3.4, 7.1 |
| 11 | Risk register (proposed) and subcontractor clause: pending team review | 5.3.7, 7.7 |
| 12 | Status of Module 2 audit items: TBD | 7.6 |
| 13 | Reference list | 2 |

[Table 9.B] Open Items

# 10.  Index

[Index to be generated in the final version.]